## Admin Web
Title | Description | Screenshot | Bug/Suggestions | Status | Comments
Login screen | Forget password is missing |  | Suggestions
Dashboard | Getting 0 collection error on dashboard screen | https://prnt.sc/3gTSI56a-dqZ | Bug | Closed
Dashboard | Dashboard should be interactive, boxes should redirect to respective pages. | https://prnt.sc/uKjHsRS3Egdf | Suggestions | Closed
Users List | Add dash if details not available |  | Suggestions
Users List | At Least a username search should be available |  | Suggestions |  | no search and filter option available in all listings
Users List | Listing should be visible FIFO order |  | Bug | Closed | in all listing pages
Users List | Multiple message should not appear | https://prnt.sc/sKU4_4tA9W4W | Bug | Ready to test
Users List | The column title should be written in a similar way. | https://prnt.sc/xAOJIdFICla5 | Suggestions | Closed | in all listing pages
Users List | Country code not visible in listing | https://prnt.sc/18LbttJd6fas | Bug | Closed
Users List | Add some spacing | https://prnt.sc/kGY_L098mf2C | Bug | Closed | in all listing pages
User Details | Admin icon and name not visible | https://prnt.sc/bJmYm5JiHQb9 | Bug | Closed
User Details | Text alignment | https://prnt.sc/966JYeAIswXZ | Bug | Ready to test
User Details | Remove comma | https://prnt.sc/GXg7XHxWA63e | Bug | Closed
User Details | Showing create time in both time. No option to enter birth time | https://prnt.sc/T77g6PtE6oLG | Bug | Closed
User Details | Country code missing | https://prnt.sc/XlgLAMyvOeJM | Bug | Closed
User Details | University not visible |  | Bug | Closed
User Details | Remove subscription box after confirm with UT | https://prnt.sc/qHSECofnYBou | Suggestions | Closed
User Details | If any data not available please show NA | https://prnt.sc/KcRe4K0685hF | Suggestions
Update Profile | UI - Input box size should be same | https://prnt.sc/HIajlX_rfj1A | Bug | Inprogress
Update Profile | Asterisk sign should be last letter of word | https://prnt.sc/geK2nedqcvbs | Bug | Inprogress | all pages
Offers | Add s in offer | https://prnt.sc/yu-nC1bKrp-L | Bug | Closed
Add offer | Mention off in either % or amount | https://prnt.sc/XsGzIEXpsiXh | Bug | Closed
Add offer | Did not understand, use of minimum member. | https://prnt.sc/XsGzIEXpsiXh | Suggestions |  | Please change it to maximum number
Add offer | Description - spelling mistake | https://prnt.sc/EorYQuc7HaOV | Bug | Closed
Add offer | Action button should be always on right hand side | https://prnt.sc/Mm6iZIU3-x40 | Suggestions |  | all pages
Event | From where i can create event |  |  | Inprogress | Only frontend option
Post | From where i can create post |  |  | Inprogress | Only frontend option
Contact Us | Message not manage properly | https://prnt.sc/svcLsCqTnoRE | Bug | Closed
Contact Us | Listing should be visible FIFO order |  | Suggestions | Ready to test
FAQ | FAQ should be in capital letters | https://prnt.sc/oz9VkvF183nm | Bug | Closed
FAQ | Message not manage properly | https://prnt.sc/Ya523-vRuSP_ | Bug | Closed
Setting | UI | https://prnt.sc/AR1EOP7lgaD- | Bug | Ready to test
Setting | Unable to view the uploaded image | https://prnt.sc/frzunn9StZ43 | Bug | Closed
Setting | Offer image should be visible in listing like other options | https://prnt.sc/49uRkPW7KGyv | Bug | Closed
Logout | Logout popup missing |  | Bug | Closed
Offers | Active and inactive not working |  | Bug | Closed
Offers | Add - Currency missing | https://prnt.sc/6yK_ksGQTNzU | Bug | Closed
Report Log | Report log missing | https://prnt.sc/9KbwySO8MFLJ | Bug | Ready to test
Feedback log | Feedback log missing |  | Bug | Ready to test

## Website
Title | Description | Screenshot | Bug/Suggestions | Status | Comments
Home | header menu disappeared, if we reduce the screen size | https://prnt.sc/cjZngf2JrlUE | Bug | Closed
Home | UI - website main title alignment disturb | https://prnt.sc/0Yyf7gc9At6L | Bug | Closed
Home | Button should be center align | https://prnt.sc/qM6u-d-X6v0a | Bug | Closed
Home | UI - Whitespace not manage | https://prnt.sc/fLWUocu8RcVw | Bug | Closed
Home | Login option not available |  | Suggestions
Privacy policy | Header menu not visible | https://prnt.sc/FFbM8Hh6nSze | Bug | Closed
Term and Condition | Header menu not visible |  | Bug | Ready to test
FAQ | Header menu not visible | https://prnt.sc/93dWYV8jwqO_ | Bug | Closed
FAQ | Add some spacing | https://prnt.sc/93dWYV8jwqO_ | Bug | Closed
FAQ | UI - Text disappear under header menu | https://prnt.sc/4ccaVayxeHSz | Bug | Closed
Blogs | When open side menu, UI disturb | https://prnt.sc/PRjjAK7ADLy7 | Bug | Closed
Blogs | No data found message missing | https://prnt.sc/lEFuc7sidEeZ | Bug | Ready to test
Blogs | Searching should work after 3 letters. | https://prnt.sc/Z_TfI6hu-ZJT | Bug | Ready to test
Blogs | Search clear option missing |  | Bug | Ready to test
Blogs | Title not visible properly if we reduce the screen size | https://prnt.sc/gue5juAEl5sw | Bug | Closed
Blogs | The button, description, and title positions should be symmetrical. | https://prnt.sc/mQYFIsW6mThY | Bug | Closed
Blogs | Filter tab not working, if data not available | https://prnt.sc/i8c3yOx3Ov1q | Bug | Ready to test
Blogs | Taking too much time to load data, can we add a load | https://prnt.sc/tUM81v2Af4sS | Suggestions | Ready to test
Blogs | If user click on about us, page should auto scroll to about us section on home page |  | Bug | Ready to test
Blogs | Add some padding | https://prnt.sc/tUXdjEe3N83W | Suggestions | Closed
Blogs | UI disturb | https://prnt.sc/fvflIURKSmhH | Bug | Closed
Blog | On load showing invalid date,invalid should not visible |  | Bug | Ready to test
Blog | Text UI disturb | https://prnt.sc/7nN5J09ijDsE | Bug | Closed
Blog | UI | https://prnt.sc/6PpRzlflWQvp | Bug | Ready to test
Subscription | On click subscription button, did not getting successful message |  | Bug | Closed
Subscription | On click subscription button, field should be clear |  | Bug | Closed
Subscription
Subscription
Blog

## User Web
Title | Description | Screenshot | Bug/Suggestions | Status | Comments
Sign - up | In sign up getting error, account already exists but i already deleted the card. | https://prnt.sc/HfQbFaLZYTd5 | Bug | Closed
Sign - up | Did not check, unable to create new account, not received otp mail. |  | Bug | Closed
Sign - up | Email and location field - asterisk sign is missing | https://prnt.sc/mdGKuWCKHyFx | Bug | Closed
Sign - up | Last name - validation error message missing | https://prnt.sc/mdGKuWCKHyFx | Bug | Ready to test | Asterisk
Sign - up | First name - Incorrect error message | https://prnt.sc/mdGKuWCKHyFx | Bug | Closed
Sign - up | DOB - User should not able select date less than 18 years old | https://prnt.sc/wv_lsW09mmWR | Bug | Closed
Social Sign-up - Height | Selection direction working opposite | https://prnt.sc/oGE83QkG0Ioo | Bug | Closed
Social Sign-up - Uploads photos | Able to upload audio in place of video. add validations | https://prnt.sc/YOx6qyjrJL57 | Bug | Closed
Social Sign-up - Uploads photos | Selected file name should be visible | https://prnt.sc/YOx6qyjrJL57 | Bug | Closed
Social Sign-up - Uploads photos | How i can upload 4 photos | https://prnt.sc/qPESCWmAb6vQ | Bug | Closed
Social Sign-up | Error messages should be proper with relative to quation | https://prnt.sc/L40xJ44y-6XP | Bug | Ready to test
Home | Dashboard - UI disturb | https://prnt.sc/uCk7Wfcq9e0Z | Bug | Ready to test
Home | Side arrow not working | https://prnt.sc/GnS-h-cKNI1c | Bug | Closed
Home | False data visible. did not make category for offer from admin web | https://prnt.sc/lbLEghzozKO_ | Bug | Closed
Home | No data message missing | https://prnt.sc/TY9vXDwXqt1g | Bug | Ready to test
Home | UI - Icon and text do not respond to mouse hover | https://prnt.sc/hjgimkdbcBdE | Bug | Ready to test | Icon colour should also change
Home | Background scroll also visible with pop-up scroll | https://prnt.sc/ra2E2B_38EvG | Bug | Ready to test
Home | SOS - send not working | https://prnt.sc/ITRLuXytRZWh | Bug | Ready to test
Home | Sos - On click submit button, popup should be closed. | https://prnt.sc/nReDqUhWSxFy | Bug | Closed
Home | SOS - Getting multiple notifications. | https://prnt.sc/DgASS0kT-WwF | Bug | Closed
Home | Filter slide should closed when user clicks outside | https://prnt.sc/4vcmXb6IBzOg | Bug | Closed
Home | Notification and profile dropdown should be closed when user clicks outside | https://prnt.sc/4vcmXb6IBzOg | Bug | Closed
Home | Notification - Clear and read option missing | Screenshot by Lightshot | Suggestions
Home | Unable to read complete notification text | https://prnt.sc/7aHxUIsssBhw | Bug | Closed
Home | Notification - Count missing |  | Bug
Home | Notification - Title missing on pop-up | https://prnt.sc/8O6l2_cBInsd | Bug | Closed
Home | UI - Filter - add some spacing if no matches found | https://prnt.sc/Eg62GMOovRnj | Bug | Ready to test | Add some space
Home | Filter - If no matches found on search so a proper message. like No matches found. | https://prnt.sc/Eg62GMOovRnj | Suggestions | Ready to test
Home | Filter - Unable to use distance and age filter, asking for upgrade plan |  | Bug | Closed | By default user register then have basic plan and when when user filter above range then redirect upgrade plan
Home | Filter - Why we are showing false data, please remove. | https://prnt.sc/KJrrlQReqNlf | Bug | Closed | This is dynamic data and first time show according to plan
Home | UI - Filter - Reset button not working, data not visible |  | Bug | Ready to test
Home | Filter - Range should be always 0-something, please remove icon and fixed lower point | https://prnt.sc/46Umic70WpLk | Bug | Closed
Home | Find User - UI - Listing | https://prnt.sc/G13V7BlCHmaY | Bug | Ready to test
Home | Offer - Show only one offer, rest will be visible on offers screen | https://prnt.sc/BqZnx3Mt9qxb | Bug | Closed | Pease check figma and i am showing 4 offers on dashboard page and reset will be visible on offer page
Home | When i upload image from mobile app, web complete disturb. eg - event | https://prnt.sc/PyiWyl_rzE8S | Bug | Ready to test | Please manage images in all screens
My Account | Unable to access my video, which upload at the time of sign up |  | Bug | Closed | Please check on your profile
My Account | Multiple success message should not received | https://prnt.sc/H4Flbc07P1Hf | Bug | Closed
My Account | UI - remove extra space | https://prnt.sc/4FGhXzyrM2lP | Bug | Ready to test
My Account | Showing wrong units in height. Should show value and unit title should be same. if show value if feet then mention feet unit. | https://prnt.sc/xP_un-1gt59F | Bug | Closed
My Account | Edit height - not working properly. select 7 feet but showing height 4.4 feet. | https://prnt.sc/924Yt3ndXMWB | Bug | Closed
My Account | Update account - getting multiple success message | https://prnt.sc/w1VAgcbLHdMR | Bug | Closed | Please manage on all action button
My Account | Unable to update self address |  | Bug | Closed
My Account | Manage space properly in love style question. |  | Suggestions | Ready to test
My Account | Profession type question missing | https://prnt.sc/SihJo5QaTlAO | Bug | Closed
My Account | No option available to update profile image |  | Bug | Ready to test
My Account | Should show height in the height bar | https://prnt.sc/X3ouEWtLOKHV | Bug | Closed
My Account | Gender icon should be update as per selection | https://prnt.sc/_bJdYIWYHjX3 | Bug | Closed
My Account | Multiple questions are missing, please match with app. like marital status, child, child age etc. |  | Bug | Closed | Only select single
My Account | On every edit pop-up, quotations missing. | https://prnt.sc/cB6J3pywBM7H | Bug | Closed
My Account | Incognito not working, user visible in suggestion | https://prnt.sc/WRzmwCG4kgVF | Bug | Closed | No need to do
My Account | Phone no should be optional throughout the web | https://prnt.sc/Aq9a6eADQFLj | Bug | Closed | Sign-up screen
User profile | Match % not visible | https://prnt.sc/EFO85-zxKBDm | Suggestions | Ready to test
User profile | UI - Left align | https://prnt.sc/MYEZ4Og2zjlE | Bug | Closed
User profile | Centimeter not visible | https://prnt.sc/9vHMPL4D2fIm | Bug | Closed
User profile | Data not visible | https://prnt.sc/SA3CxFXhlOR3 | Bug | Closed
User profile | All fields are not visible ? (ask 24 questions) |  | Bug | Closed
User profile | Form should be clear after sending the interest | https://prnt.sc/fUiQ2pzNlWC5 | Bug | Closed
User profile | Show interest button text should be changed once interest already show | https://prnt.sc/9-r3T7N7pXpd | Bug | Closed
User profile | UI | https://prnt.sc/XCTKWmpeYs_E | Bug | Ready to test
User profile | Graph should be in green colour and fill as per % profile match.like in app | https://prnt.sc/YYHm2P-9vRO0 | Bug | Ready to test
User profile | UI | https://prnt.sc/osMKjd4fjD1p | Bug | Ready to test | In all pages where the profile match graph is visible
User profile | Where i can see the my interested people list | https://prnt.sc/uNl1vkMl1ThL | Bug | Inprogress | Need discuss and not in figma
Matches | UI on scroll | https://prnt.sc/yZg6qHNWVPtf | Bug | Ready to test
Matches | UI | https://prnt.sc/D7g4umOplxVh | Bug | Ready to test
Matches | UI | https://prnt.sc/7eCf84dCiSPU | Bug | Ready to test
Matches | Header menu position should be fixed on any screen. | https://prnt.sc/xavu8CfAgLPV | Bug | Ready to test
Matches | UI - Send message input box and user profile | https://prnt.sc/5gPTlmOz9Qt2 | Bug | Ready to test
Matches | Please should last active status, now user just showing time. | https://prnt.sc/_ZNW6OU0J_Ml | Bug | Ready to test
Matches | No chats message missing | https://prnt.sc/Xu5Y82lvgRnO | Bug | Inprogress | Need Discuss and not in figma
Matches | Call not working, how it will work | https://prnt.sc/t_dq6MWoZ8DF | Bug | Closed
Matches | By default one should be selected | https://prnt.sc/zDySYU-JihRC | Bug | Inprogress | Need Discuss
Event | No events message missing | https://prnt.sc/_LoJAcKJij1r | Bug | Closed
Event | Unable to create event. need to purchase plan, but subscription part is already removed. | https://prnt.sc/SOFXmVgmUkSm | Bug | Closed
Event | On search, if no data available. show proper message. | https://prnt.sc/g68fM8R4DSnV | Bug | Closed
Event | On enter, search box should not be clear |  | Bug | Closed
Event | Search box clear option is missing | https://prnt.sc/k2CMCGdXKZ3e | Bug | Ready to test
Event | Searching should work after 3 letters. |  | Bug | Closed
Event | Search bar position not affect on search result quantity . Search bar change its position if no data available | https://prnt.sc/p-NVJK3dWKAz | Bug | Closed | please check all places
Event | Unable to like/dislike |  | Bug | Closed
Event | Title should be visible in 1 line | https://prnt.sc/7yDUR2wEIkxv | Bug | Ready to test
Event | All event tiles should be same size | https://prnt.sc/LLanJYUT4hKe | Bug | Ready to test
Event details | Unable to like/dislike | https://prnt.sc/mxQFzu5tJVCa | Bug | Closed
Event details | Manage spacing properly | https://prnt.sc/w77PtyIF-fn6 | Bug | Ready to test
Event details | Remove event create button from detail screen | https://prnt.sc/tNmvjDiCIVVn | Bug | Closed
Event details | Event date not visible | https://prnt.sc/tNmvjDiCIVVn | Bug | Closed
Event details | Event name and location visible 2 times | https://prnt.sc/awxEOt-CCLZc | Bug | Closed
Event details | Event details screen not match with figma |  | Bug | Closed
Event details | Edit and delete option missing |  | Suggestions
Event details | Please manage minimum and maximum image size. if text is small, image become a line | https://prnt.sc/ATyMYKvXOImJ | Bug | Ready to test
Event details | AM and PM missing in start and end time | https://prnt.sc/ATyMYKvXOImJ | Bug | Closed
Create Event | Add asterisk signs on mandatory fields | https://prnt.sc/JxUA6dla9zql | Bug | Closed
Create Event | Error message should be outside input box | https://prnt.sc/IbDrOvYWgXNq | Bug | Closed
Create Event | Text not visible, please manage white space properly | https://prnt.sc/kFwkjKdyCIih | Bug | Ready to test
Create Event | On click create, multiple event should not be create. Add loader or disable button | https://prnt.sc/O-cW7nLsdbEC | Bug | Closed | please manage on all add and edit pages
Create Event
Offers | UI - Showing 2 offers in one box and from where i can add main image | https://prnt.sc/lOmsLps_H-DS | Bug | Ready to test
Offers | If image is not supported or not available, please 'no image' image | https://prnt.sc/L6VYwUp1-alS | Bug | Closed
Offers | UI - disturb - text wrap | https://prnt.sc/5jYdaKy_RS_O | Bug | Ready to test
Offers | Title not visible |  | Bug | Closed
Offers | Inactive offers are visible | https://prnt.sc/99c39QyiF2u8 | Bug | Closed
Offers | Please increase offer image size | https://prnt.sc/-g9hNLcLk_kJ | Suggestions | Ready to test
Offers | Detail popup - title is missing | https://prnt.sc/XByvBGwPxbqV | Bug | Closed
Subscription Plan | Hide subscription option everywhere. | https://prnt.sc/hXS0w9T07irR | Bug | Closed
Logout | Add question mark sign. | https://prnt.sc/PvJ_ByUOXTeA | Suggestions | Closed
Forget Password | did not getting OTP on mail | https://prnt.sc/KNjZMYIyU0_k | Bug | Closed
Who view profile | Unable to check, who view my profile. Neither working nor giving any error message. | https://prnt.sc/mi302pXRGFpB | Bug | Closed
Who view profile | Unable to check |  | Bug | Closed
Post | UI - disturb | https://prnt.sc/WcE6WpB3xCjG | Bug | Ready to test
Post | No need to update time of every post, every sec without refresh | https://prnt.sc/BleRY9CiNF2l | Bug | Closed
Post | Unable to access all images and videos of post |  | Bug | Closed
Post | Unable to update images and video of any post | https://prnt.sc/oizbSBC20h8h | Bug | Closed | No option to update
Post | No need to update time of every comment, every sec without refresh | https://prnt.sc/UDC6IzTjeuAn | Bug | Closed
Post | Old post comment visible on new post, when add new post |  | Bug | Closed | Issue not found
Post | Post comments should be visible in FIFO order | https://prnt.sc/1w7fJr2r5ph8 | Bug | Ready to test
Post | On click any commenter profile icon, redirect to that user profile. | https://prnt.sc/GMMDQ-B__JQA | Bug | Closed
Post | If comment on new post, old post comments disappear | https://prnt.sc/WMxciVmgtmaD | Bug | Closed
Feedback | Please remove unwanted icon | https://prnt.sc/Kvsmt9tgMfSo | Bug | Closed | Please check figma
Feedback | Spelling mistake - In Feedback, b should be small | https://prnt.sc/WqtSJOJWV9jU | Bug | Closed
Feedback | UI disturb | https://prnt.sc/qB6sqJaf_saN | Bug | Ready to test
Feedback | Submit button text alignment | https://prnt.sc/s8iOBPJ0aAsT | Bug | Ready to test
Feedback | After successfully submitted, form should be clear (rated star) |  | Bug | Closed
Settings | UI disturb | https://prnt.sc/rVv5mZOksMBB | Bug | Ready to test
Settings | Logout link available 3 places, remove 2 option | https://prnt.sc/hwrfStu-BjrY | Bug | Closed | Please check figma
Privacy Policy | Data not visible as formatted, like title are bold. | https://prnt.sc/5frTXSHmJxZR | Bug | Ready to test | Change on admin panel
Give Feedback | Wrong icon used | https://prnt.sc/mJcKJO4Z3OoC | Bug | Ready to test
Give Feedback | Should able to give rating in half stars. like 2 and 1/2 | https://prnt.sc/7gKAS8QdgRCE | Bug | Closed | In app, we can able to give (check)
Give Feedback | Did not understand text, at the booking. Can you please remove it. | https://prnt.sc/G76pBcYqpAh4 | Bug | Closed
Sign up | Getting error when resend password | https://prnt.sc/QH1tV5ZvJdJ- | Bug | Closed
Sign up | Add loader on sign up submit button |  | Bug | Closed
Sign up | If send multiple OTP, unable to login with all received OTP |  | Bug | Closed
Home | Age filter working |  | Bug | Closed
Home | Filter - Able to select multiple 'Interested in' options |  | Bug | Closed
Home | Filter - Able to select multiple 'Looking for' options |  | Bug | Ready to test
Home | Filter - Able to select multiple 'Education Level' options |  | Bug | Ready to test
Home | Showing wrong details in fresh account, when try to login again. |  | Bug | Ready to test
SOS | On click send, user should get success or fail message and on success popup should be closed |  | Bug | Ready to test
Feedback | Remove LTd | https://prnt.sc/xA0M6XKbSWu0 | Bug | Ready to test
Home |  |  | Bug
Match up | Chat - UI - disturb | https://prnt.sc/AcPehnI1WJtd | Bug | Ready to test
Match up | Show user complete name, if long show dots in last | https://prnt.sc/aCX6RuYYHF8a | Bug | Ready to test
Match up | Chat - UI - If user not started any conversation , show the left hand message in chat message place | https://prnt.sc/aCX6RuYYHF8a | Bug | Inprogress
Match up | Chat - Different users chat visible in different user. | https://prnt.sc/SQCnImrr0CNU | Bug | Ready to test
Match up | Chat - Unread message count is not update, should be disappear if user open that person chat | https://prnt.sc/SQCnImrr0CNU | Bug | Ready to test
Match up | Report and block popup should be closed on click outside the popup | https://prnt.sc/kCfNwio1pReq | Bug | Ready to test
Match up | Showing message sending time, please show how much time before i sent the message. | https://prnt.sc/h_UNPJ3YJYKM | Bug | Closed
Match up | UI - Chat - Show profile selected whose chat screen is open |  | Bug
Match up | Chat - message should be autoscroll, show the latest message. not working if we manual screen chat. |  | Bug | Ready to test
Match up | Add confirmation popup on report and block click | https://prnt.sc/pXZ7Bd-Vbisj | Bug | Ready to test
Match up | UI - Chat - Add some space at bottom, text and scroll bar always above the send message box | https://prnt.sc/AJ8d4zbrC7Wu | Bug | Ready to test
Event | Blanck search not working |  | Bug | Ready to test
Event details | Showing wrong date | https://prnt.sc/5ZMaRkvmWCBR | Bug | Ready to test
Who view profile | Show user complete name, if long show dots in last | https://prnt.sc/PLROc8wUM7AY | Bug | Ready to test
Post | Showing post time in minus | https://prnt.sc/e7nULhH1M6xs | Bug | Ready to test
Post | Showing comment time in minus | https://prnt.sc/QiaGJuEDoAIN | Bug | Ready to test
Chat | UI - If user scroll, request button not working | https://prnt.sc/PIf47FZU6KsY | Bug | Ready to test
Post | UI - Video should be center align | https://prnt.sc/28gxAWX_FgYv | Bug | Ready to test
Bug
Bug
Bug
Bug
Bug

## Android App
Title/ Module | Description | Screenshot | Bug/Suggestions | Status | Comments
Login | Social login is missing | https://prnt.sc/ZxtLCMfo3QhW | Bug | Inprogress | It is temporarily removed because of app store.
Forget Password | Not working | https://prnt.sc/wO_WGhADNRSG | Bug | Inprogress | Backend Response
Signup | Not working, unable to test |  | Bug | Inprogress | OTP service need to be restored from backend
Signup | DOB - User should not able select date less than 18 years old |  | Bug | Closed | Done
Edit Profile | If user have mobile no, should be visible pre-filled. |  | Bug | Closed | Working on my end
Edit Profile | Gallery option is missing in update profile photo. |  | Bug | Closed | Done
Edit Profile | In every text box, editable value should be darker and non-editable should be lighter. |  | Bug | Closed | All add and edit form(Done)
Edit Profile | DOB - User should not able select date less than 18 years old |  | Bug | Closed | Done
Edit self description | Button text should be update, not next. | https://prnt.sc/knNqwdBPo2Hv | Bug | Closed | Done
Edit self description | Increase description text window size as per device screen |  | Suggestions |  | NTD
Edit self description | Should able to change interested gender |  | Suggestions
Edit self description | Title should be edit description |  | Bug | Closed | Done
Edit Hobbies | Title should be edit hobbies |  | Bug | Closed | Done
Edit Hobbies | Doing staff option missing in app | https://prnt.sc/eU1XPpm-W2Fc | Bug | Closed | As per UT request, It was removed
Edit Hobbies | Button text should be update, not next. | https://prnt.sc/W6gE6DGG1XI1 | Bug | Closed | please check in all pop-ups
Edit photos | Video part not working |  | Bug | Ready to test | Working on my end, please provide way for regeneration
Edit photos | Change photo/video, gallery option should be visible |  | Bug | Closed | Added Gallery Option for photos but for videos as IT said there will be only camera
Edit photos | Have a message, upload at least 3 photo's,how i can upload 4 or more photos. |  | Suggestions |  | NTD
Send SOS | Not working |  | Bug | Inprogress | Working on my end, please provide way for regeneration
Home | Notification - Count missing |  | Bug | Closed | It is shown when you have any unread notification
Home | Filter - Should able to select one interested in option at a time | https://prnt.sc/PFmLHuypl-dJ | Bug | Inprogress | Coordinate with manish before any change, should have same functionality.(This is Done as per requested by UT)
Home | Should able to select one option at time in looking for | https://prnt.sc/c_yU4czGEZeL | Bug | Inprogress | Coordinate with manish before any change, should have same functionality.(This is Done as per requested by UT)
Home | Should able to select one option at time in Education Level |  | Bug | Inprogress | Coordinate with manish before any change, should have same functionality.(This is Done as per requested by UT)
Give Feedback | Spelling mistake - In Feedback, b should be small |  | Bug | Closed | Done
Give Feedback | Page title missing |  | Bug | Closed | Done
Give Feedback | Add a validation on star select, user must select the star. |  | Bug | Closed | What if user wants to give zero stars?
Events | Unable to like/dislike |  | Bug | Closed | UT verified
Events | Title should be visible in 1 line | https://prnt.sc/7yDUR2wEIkxv | Bug | Closed | Done
Events | Images taking too much time to load, please show reduce size image |  | Bug | Inprogress | It depends on uploaded file size and user internet connection
Event details | Unable to like/dislike |  | Bug | Closed
Event details | Event name and location visible 2 times | https://prnt.sc/_GJVut1OLlMA | Bug | Closed
Event details | Showing static content | https://prnt.sc/_GJVut1OLlMA | Bug | Closed | Arrive on time before 5 min will always be there so it is static.
Event details | Event details screen not match with figma |  | Bug | Closed | It was later changed so it does not match
Event details | Edit and delete option missing |  | Suggestions |  | NTD
Event details | AM and PM missing in start and end time |  | Bug | Closed | Showing on my end. please provide a screenshot
Create Events | Button text should be create or submit not update. | https://prnt.sc/NlIwT6zEZhf5 | Bug | Closed | Done
Create Events | Getting validation error for option field | https://prnt.sc/tV_fAGxSOrEK | Bug | Closed | Done
Create Events | Add front end validation for event name field with proper error message | https://prnt.sc/Yzsyo2edEtMF | Bug | Closed | Done
Offer Details | Showing static text | https://prnt.sc/B3Yyv6UYlnbx | Bug | Closed | It was in UI, now removed.
User Offers | Images should be left align as per figma | https://prnt.sc/2EdQyFpCmdIk | Bug | Discussed | Tried but not possible as different dimension of images make it align in center
Post | Getting error while playing video | https://prnt.sc/m9UPNaw5ublm | Bug | Ready to test | Added validation for larger video size
Post | Dislike l should be small | https://prnt.sc/ne-hXVV_hPoF | Bug | Closed
Post | In dislike icon, green colour should be filled like as like icon |  | Bug | Closed
Post | Comment section not working properly |  | Bug | Closed | please provide brief description about it. At my end it is working.
Post | If comment on new post, old post comments disappear |  | Bug | Closed
Post | On click any commenter profile icon, redirect to that user profile. |  | Bug | Closed
Post | Manage white space, as in figma | https://prnt.sc/67pu0_sE0oEW | Bug | Closed
Post | Alignment - Text should be left align and icon start and end point should be same | https://prnt.sc/s0nLpRJHX7V3 | Bug | Closed
Post | Public feeds and My feeds - On tab switch, screen should be load. |  | Suggestions
Add Post | Give some space | https://prnt.sc/TUKSNpSulMN8 | Bug | Closed
Edit Post | Confusing UI, either make a popup or add margins to user can identity. | https://prnt.sc/Wl0r0H39UCP2 | Bug | Closed | Added Space
Edit Post | Unable to change image and video |  | Bug | Closed | you can only edit caption like instagram
Chats | Call - Not working, how it will run. |  | Bug | Closed | It will redirect you to your device dialer
Chats |  |  | Bug
Bug
Onboard Screen | Short description text missing, same for next 2 screen also | https://prnt.sc/fZqFzWK39B7- | Bug | Closed | It was removed by UT
Sign up | Give some space | https://prnt.sc/WWhvIEURPO8G | Bug | Closed
Sign up | Add validation for mobile no | https://prnt.sc/jEYnoNbHrvzc | Bug | Closed | Mobile Number is Optional
Sign up | Add validation error message if user not accept T&C . | https://prnt.sc/jEYnoNbHrvzc | Bug | Closed | If User has not accepted T&C then he will not be able to click button as it is disabled
Sign up | On click 'User License Agreement' , redirect to T&C, please check is this correct | https://prnt.sc/jEYnoNbHrvzc | Bug | Closed
Sign up | Did not getting validation errors, please check all fields. |  | Bug | Closed
Sign up | Sign up, button not working |  | Bug | Inprogress
Home | Location not working properly, i change my location but KM not change. how it is working | https://prnt.sc/wSwhkr5kSwJl | Bug | Closed
Home | Should show city and country | https://prnt.sc/xG8GTuO9VYOI | Bug | Closed
Home | User profile is not verified, icon should be removed | https://prnt.sc/HL2IiPFN7Vtu | Bug | Closed
User details | Should show city and country | https://prnt.sc/1KmApUf-7-ku | Bug | Closed
Chat | Request - Unable to see reject list |  | Bug | Discussed | NTD
Chat | First time chat - Message change to send your first message |  | Bug | Closed
Chat | Reported and Blocked - unable to reconnect |  | Bug | Discussed | NTD
Chat | Adblock confirmation popup |  | Bug | Closed
Chat | When keyboard is open, chat should be auto scroll |  | Bug | Closed
Chat | Chat delete pe list refresh second user pe |  | Bug | Discussed
Who view my profile | Title should be center align |  | Bug | Closed
Who view my profile | Showing 'show interested' button in already connected person details |  | Bug | Closed
Home | Filter - Location not working |  | Bug | Closed
Create Event | Date format should be DD/MM/YYYY |  | Bug | Closed
Event | Event name and location visible 2 times on event detail screen |  | Bug | Closed | As Discussed with utkarsh sir i am showing event name and venue on both sides as we dont have much data
Event | Like/dislike not working |  | Bug | Closed | As Discussed with utkarsh sir there was no functionality for like and dislike in events
Event | Searching should work after 3 letters. |  | Suggestions | Discussed
Feedback | Where i can see feedback ? |  | Bug | Inprogress | NTD
Event | App crash on event screen when put phone ideally |  | Bug | Closed | Image size needs to be reduced from backend... and from my end i am loading only 5 events at a moment
Bug
Bug
Bug
Bug
Bug
Bug
Bug
Bug
Bug
Bug
Bug
Bug
Bug
Bug
Bug
Bug
Bug
Bug
Bug
Bug
Bug
Bug
Bug
Bug
Bug
Bug
Bug
Bug
Bug
Bug
Bug
Bug
Bug
Bug
Bug
Bug
Bug
Bug
Bug
Bug
Bug
Bug
Bug
Bug
Bug
Bug
Bug
Bug
Bug
Bug
Bug
Bug
Bug
Bug
Bug
Bug
Bug
Bug
Bug
Bug
Bug
Bug
Bug
Bug
Bug
Bug